## Regional Acute Care Hospital Expansion

- Project: Regional Acute Care Hospital Expansion

- Target estimate value: USD 285M (concept range: USD 255M-315M)

- Location: Phoenix, Arizona, USA

- Contract type: GMP (CMAR)

- Delivery timeline: Notice to Proceed in Q3 2026, Substantial Completion in Q1 2029

- Scope summary: 220,000 sq ft vertical expansion, OR suites, MEP upgrades, active campus logistics, phased occupancy

## Executive Summary

The conceptual estimate risk posture is moderate-to-high at this stage, with primary exposure concentrated in market pricing volatility, live-campus productivity impacts, and scope definition maturity for complex MEP/clinical interfaces. Based on historical comparables in similar value bands and contract type, the likely risk direction is upward on both cost and schedule unless early design freeze discipline, procurement timing, and logistics planning are tightened before basis-of-estimate lock.

## Project-to-History Fit

Historical alignment is good on value and contract type and moderate on geolocation. Comparable set assumed: 11 healthcare projects (USD 180M-420M), 7 GMP, 6 in high-growth Sun Belt labor markets, with 5 completed within the last 36 months. Confidence is medium, reduced by limited direct matches on active-campus phasing complexity and recent MEP equipment lead-time instability.

## Top Estimate Risks

- Risk statement: Scope definition risk in clinical adjacency and phased turnover requirements may drive late design change.
Evidence from historical comparison: Similar healthcare expansions showed 3%-8% post-DD estimate growth where phased occupancy criteria were not fully defined at concept stage.
Likelihood/Impact: High/High.
Potential exposure direction: Cost up, schedule right.
Mitigation action: Set phased occupancy requirements by zone before 30% design; enforce design-change governance with executive escalation triggers.

- Risk statement: Quantity and takeoff risk for vertical tie-ins and existing-conditions work may understate demolition, temporary works, and rework.
Evidence from historical comparison: Projects with major tie-ins averaged 2%-5% quantity growth from concept to IFC, especially in structural and MEP enabling packages.
Likelihood/Impact: Medium/High.
Potential exposure direction: Cost up.
Mitigation action: Add targeted early intrusive investigations and package-specific quantity validation (structure, above-ceiling MEP, temporary life safety).

- Risk statement: Market and escalation risk remains elevated for electrical gear, controls, and medical gas components.
Evidence from historical comparison: Recent healthcare projects in comparable markets absorbed 4%-9% procurement variance tied to long-lead equipment timing.
Likelihood/Impact: High/Medium.
Potential exposure direction: Cost up, schedule right.
Mitigation action: Pull forward long-lead procurement strategy, prequalify alternates, and include escalation assumptions explicitly by commodity category.

- Risk statement: Labor availability and productivity risk may reduce installed productivity due to regional demand and constrained working windows on active campus.
Evidence from historical comparison: Sun Belt healthcare programs under active operations showed 8%-15% productivity drag versus greenfield baselines.
Likelihood/Impact: Medium/High.
Potential exposure direction: Cost up, schedule right.
Mitigation action: Validate labor loading assumptions by trade, add shift-premium scenario testing, and align shutdown windows with hospital operations earlier.

- Risk statement: Geolocation and logistics risk from active-campus constraints (access, infection control, noise windows) may increase indirects and sequencing complexity.
Evidence from historical comparison: Campus projects with strict ICRA and access controls showed 1.5%-4% general conditions growth and milestone slippage.
Likelihood/Impact: Medium/Medium.
Potential exposure direction: Cost up, schedule right.
Mitigation action: Build logistics simulation into preconstruction, lock material routing plans, and define contingency for controlled-access inefficiencies.

- Risk statement: Contract and commercial risk under GMP may transfer less risk than assumed if clarifications and allowances are insufficiently defined.
Evidence from historical comparison: GMP projects with immature bid packages saw allowance burn rates exceed plan by 20%-35% in first half of construction.
Likelihood/Impact: Medium/Medium.
Potential exposure direction: Cost up (through contingency/allowance consumption).
Mitigation action: Tighten commercial assumptions in bid package narratives and establish early allowance governance with monthly burn-rate thresholds.

- Risk statement: Schedule compression risk is present if owner milestone expectations force overlap before design maturity.
Evidence from historical comparison: Fast-tracked healthcare projects showed increased RFI/change velocity and 2-4 month completion pressure when overlap exceeded planned tolerances.
Likelihood/Impact: Medium/High.
Potential exposure direction: Schedule right, second-order cost up.
Mitigation action: Define non-negotiable design maturity gates before procurement release and maintain a risk-adjusted master schedule.

- Risk statement: Stakeholder decision latency risk may delay design closure across clinical user groups and facilities operations.
Evidence from historical comparison: Multi-stakeholder healthcare programs with fragmented decision rights experienced recurring redesign cycles and approval lag.
Likelihood/Impact: Medium/Medium.
Potential exposure direction: Schedule right, indirect cost up.
Mitigation action: Implement a decision-rights matrix, weekly decision log, and executive escalation for unresolved items beyond SLA.

- Risk statement: Data quality and benchmark relevance risk may bias early contingency if comparator normalization is incomplete.
Evidence from historical comparison: Cross-project unit-rate comparisons without normalization (scope, phasing, geography, timing) produced false confidence in early ROM positions.
Likelihood/Impact: Medium/Medium.
Potential exposure direction: Either direction, with current bias toward underestimation.
Mitigation action: Normalize benchmark set with explicit adjustment factors and document confidence bounds for each comparator.

## Recommended Contingency Position

A conservative-to-moderate contingency posture is recommended at this stage, with a bias toward conservative until 30% design and logistics/phasing assumptions are validated. Executive rationale: key risks are not evenly distributed; they are concentrated in known high-impact drivers (phasing complexity, long-lead procurement, and live-campus productivity), which historically generate asymmetric downside when unresolved early.

## Assumptions and Data Gaps

- This is a hypothetical sample and does not use live SharePoint records.

- Assumed comparator sample size, recency, and distribution were created for format validation only.

- Missing fields for production use:

  - Historical estimate metadata schema (currency year, escalation basis, estimate class)

  - Final awarded values vs. estimate snapshots by stage

  - Actual productivity outcomes by trade

  - Allowance/contingency drawdown history

  - Schedule baseline vs. actual milestone variance

- Follow-up data pulls recommended:

  - Last 5 years of healthcare GMP estimates in comparable value bands

  - Geolocation-adjusted labor and material indices by bid quarter

  - Package-level variance history for MEP, structural tie-ins, and temporary works